## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | No | High | Not Started | 6 | No
The Customer will enter all personal details like Name, age, sex, dob, address, employment type, employer name, salary, emi(if any),email id, gender, purpose of loan(currently only personal loan) | Yes | No | High | Not Started | 1 | No
Validate the details | No | No | High | Not Started | 1 | No
The system checks the eligibility of the user through the loan eligibility calculator. | No | No | High | Not Started | 2 | No
The eligible user will be displayed with the loan amount, tenure and rate of interest. | No | No | Medium | Not Started | 1 | No
The willing customer will click on upload documents button. | No | No | Medium | Not Started | 1 | No
Redirects to upload documents web page. | No | No | Medium | Not Started | 0 | No
Sprint 2 | No | No | Low | Not Started | 20 | No
Verification of PAN details, Govt. ID proof, id number, upload the documents. | No | No | Low | Not Started | 5 | No
Verify the documents with OCR and generate credit score | No | No | Low | Not Started | 10 | No
Sprint 3 | No | No | Low | Not Started | 5 | No
Create an account for the user, by entering all the detials in the database | No | No | Low | Not Started | 3 | No
Create a web page for the user to track the status of the loan. | No | No | Low | Not Started | 2 | No
Sprint 4 | No | No | Low | Not Started | 10 | No
Get the list of applied loans | No | No | Low | Not Started | 5 | No
Approve/Deny the loan application | No | No | Low | Not Started | 5 | No
Sprint 5 | No | No | Low | Not Started | 5 | No
Send mail/sms 1. After approval/denial of loan 2. Reminder for every month for loan payment | No | No | Low | Not Started | 5 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started